## Target
SUMMARY OPTION 6 1 IN 100 YEAR FSA WITH AUTOMATIC CONTROL
£
People
| Ganger, Labourer, Carpenter, Steelfixer |  |  |  | 137127
Equipment |  | Site establishment/small plant | 45500.4
|  | Equipment | 277112.86 |  | 322613.26
Supervision |  |  |  |  | 117055.28
Materials as Schedule |  |  |  |  | 186356.75
Services |  |  |  |  | 11052
Sums
| General Items not included elsewhere, as Summary |  |  |  | 10195
SubContractors as Schedule |  |  |  |  | 118072
Risk |  |  |  |  | TO BE CONFIRMED
902471.29
10 % Contingency |  |  |  |  | 90247.129
5% Inflation allowance for construction in 2007/08 |  |  |  |  | 45123.5645
1037841.9835
Fee 8% (as NCF 2) |  |  |  |  | 83027.3587
|  |  |  | Total | 1120869.3422

## Materials
Material | Supplier | Quantity | Unit | Rate | Price
Sub-base
Type 1 |  | 2150 | t | 17 | 36550
Crushed concrete |  | 2150 | t | 15 | 32250
Crushed concrete (site compound) |  | 1500 | t | 15 | 22500
Hoggin for spillway |  | 700 | t | 15 | 10500
Pipes
1500 dia |  | 18 | m | 250 | 4500
600 dia |  | 66 | m | 50 | 3300
20mm pipe bedding |  | 180 | t | 20 | 3600
Sandbag headwalls |  | 2 | No | 500 | 1000
300 dia pipes + flap valve |  | 1 | Sum |  | 900
Concrete
C10 (blinding) |  | 10 | m3 | 65 | 650
C30 (hardstanding & miscellaneous) |  | 40 | m3 | 70 | 2800
C40 (structures) |  | 195 | m3 | 75 | 14625
Part load charges (assume 4m3 average, therefore 33%) |  | 80.85 | m3 | 25 | 2021.25
Channel Works
Gabion baskets (3 x 1 x 1) | Maccaferri | 36 | No | 44.5 | 1602
Reno mattresses (6 x 2 x 0.3) | Maccaferri | 6 | No | 82 | 492
Delivery costs | Maccaferri | 1 | Sum |  | 100
Gravel rejects (75mm up) |  | 240 | t | 20 | 4800
Gauge boards |  | 2 | No | 60 | 120
Metalwork
Trash screen | Included in Sub-contractors
Steel stairs
Steel open grid decking
Penstock for 1500dia pipe c/w extension spindle, etc | Ham Baker | 1 | Sum |  | 8260
Kee Klamp Guardrail (1050 high) |  | 30 | m | 60 | 1800
Spillway
Enkamat 7 series (20mm thick) | Maccaferri | 2080 | m2 | 3 | 6240
fixing pins | Maccaferri | 1000 | No | 0.3 | 300
Delivery costs | Maccaferri | 1 | Sum |  | 200
Tensar SS20 Geogrid (50 x 4) | Burdens | 15 | No | 332.4 | 4986
Reinforcement
Assume 0.15t/m3 |  | 32 | t | 480 | 15360
Fabric for hardstanding |  | 100 | m2 | 2.5 | 250
Miscellaneous
Geotextile (Lotrak 1800: 450m2 roll)) | Burdens | 12 | No | 90 | 1080
Geotextile (Lotrak 1800: 450m2 roll)) | Burdens | 10 | No | 90 | 900
Mould oil x 25l | Prepour | 4 | No | 27 | 108
Spacers & Tying wire | Prepour |  | Sum |  | 500
20mm plywood sheets (formwork) x 80 No | Jewson |  | Sum |  | 750
100 x 50 sawn | Jewson | 750 | m | 1.75 | 1312.5
Sundries (nails, etc) | Jewson |  | Sum |  | 500
Jointing materials for hardstanding |  |  | Sum |  | 500
Miscellaneous |  |  | Sum |  | 1000
|  |  |  | Total | 186356.75

## Sub-contractors
Security
1700 - 0800 Mon - Fri, 24 hrs Sat & Sun
| 123 hrs / week @£9.00/hr | 26 | wks | 1107 | 28782
P1 Parapet Guardrail
| Supply & fix | 38 | m | 180 | 6840
Trash Screen, etc to structures
Supply & install trash screen, steel
stairway, open grid decking, ladder,
| stop log channels | 1 | Sum |  | 16200
(Budget price, Ermine Engineering)
Surfacing (M11 overbridge access ramp)
| 150mm thick roadbase | 400 | m2 | 35 | 14000
| 60mm thick base course | 400 | m2 | 18 | 7200
| 40mm thick wearing course | 400 | m2 | 10 | 4000
Landscaping
| Seeding | 24000 | m2 | 1.2 | 28800
| Maintenance (mowing & watering) | 6 | visits | 1000 | 6000
Fencing
| Chainlink fence to site compound | 300 | m | 20 | 6000
| Gate | 1 | No | 250 | 250
|  |  |  | Total, Subcontractors | 118072

## Site Establishment
Item | Rate/week
Site Accommodation
55kVA Generator | 310.95
Portacabin 24 x 9 (3 No) | 91.05
Mobile 22 x 8 (2 No) | 55.1
Office consumables | 100
Container 20 x 8 (2 No) | 33.1
Wheel wash | 350
Toilet ('Solo' electric unit) | 55
995.2
Other Items
Bunded Diesel Tank & Pump (£0.70/hr) | 28
Heras Fencing (500 panels@£0.17/day each) | 425
Dust suppression bowser | 75
Diesel Bowser (£0.58/hr) | 23.2
Water Bowser (£0.58/hr) | 23.2
574.4
Small Plant Items
CAT & Genny (£0.74/hr) | 29.6
Partner Saw (£0.60/hr) | 24
2" Pump c/w 20m hoses (£1.55/hr) | 62
115.6
| Total per week | 1685.2
| x 27 weeks | 27
| Total, Site Establishment | 45500.4

## Services
Telephone
| Connection charge | (allow for poles, etc) |  |  | 2000
| Weekly call costs |  |  | 100
| Weekly allowance for mobile calls |  |  | 50
|  |  | x 27 weeks | 27
4050
Electricity
Included in site establishment costs (generator)
| Running costs, say 50 litres gas oil per day (7 days/week) |  |  | 18
|  |  | x 189 days | 189
3402
Water
| Connection charge |  | assume |  | 1000
| Monthly charge |  | assume | 100
|  |  | x 6 months | 6
600
|  |  |  | Total, Services | 11052

## Supervision
CONTRACTS MANAGER
Pre-commencement | Meetings, liaison, plan set up, method statements, etc |  |  | 5
Construction Period | Regular Supervision & management, site visits, etc. | 1/2 days/week | 27 Weeks | 14
| Monthly Progress Meetings | 1 day/month | 6 Months | 6
Post Completion | Project Handover and close-out |  |  | 3
|  |  |  | 28 | 395.28 | = | 11067.84
PROJECT MANAGER
Pre-commencement | Programming, liaison, handover to construction, Instruction to NCF |  |  | 5
Construction Period | Monthly Progress Meetings to coincide with project meetings | 1 day/month | 6 Months | 6
Post Completion | Monitoring etc during Maintenance Period |  |  | 5
|  |  |  | 16 | 267.68 | = | 4282.88
SITE AGENT
Pre-commencement | Meetings, liaison, plan set up, method statements & risk assessments, etc | 1.5 wk lead-in |  | 7
Construction Period | Regular full-time Supervision, site administration & management, etc. | 100% | 135 | 135
Post Completion | As built information, complete H & S Plan, etc |  |  | 5
| Project close-out |  |  | 2
|  |  |  | 149 | 258.16 | = | 38465.84
GENERAL FOREMAN
Construction Period | Regular full-time Supervision, site administration & management, etc. | 100% | 135 | 135
|  |  |  | 135 | 225.92 | = | 30499.2
Site Engineer | Full time |  |  | 135
|  |  |  | 135 | 150.88 | = | 20368.8
Chain Person | Full time |  |  | 135
|  |  |  | 135 | 60.32 | = | 8143.2
QUANTITY SURVEYOR
Pre-commencement | Finalise sub contract, set up cost reports & reporting procedures |  |  | 2
Construction Period | Monthly Progress Meetings, interim assessments | 2 days/month | 6 Months | 12
| Subcontract payment, internal company costs and reports | 1 day/month | 6 Months | 6
Post Completion | Retention releases, final account & close out |  |  | 2
|  |  |  | 22 | 192.16 | = | 4227.52
[5 empty] | TOTAL |  | 117055.28

## Additional items
Other items to be included
Cost
Transport costs
General plant to and from JBC Depot
|  | say 10 trips each way @ 8 hrs | £350 each x 20 No | 7000
| Toilet |  | £100 each way | 200
| Wheel wash | Install & remove | £1000 each way | 2000
Office Set-up
Electrical wiring + connection/disconnection
|  | Labour | 300
|  | Travelling | 75
|  | Materials (inc.security lighting) | 620
995
|  |  | Total, Additional Items | 10195

## Track on top of embankment
Details of proposed track on top of flood storage embankment
Labour & plant (from MS Project resourced programme) |  |  |  | 12262.05
Materials: | Crushed concrete sub-base |  |  | 32250
| Geotextile |  |  | 900
45412.05
|  | Fee | 8% | 3632.964
49045.014

## Assumptions & Qualifications
1) | Land for compound available free of charge
2) | Excavated material is not contaminated or hazardous
3) | Topsoil on existing fields assumed 300mm thick
4) | Material excavated from pond area is suitable fill for flood storage embankment
5) | 1m3 of cut = 1m3 of fill
6) | No import or off-site disposal of earthworks materials
7) | Pond size to suit material required for embankment
8) | No allowance for telemetry equipment
9) | No allowance for landscaping apart from grass seeding
No risk allowances included
Note: Concrete for structures increased from Option 5 to allow for higher and
inlet & outlet structures